## ENG Engineering Change Orders
Organization Code | Change Notice | Change Type | Change Status | Approval Status | Priority | Reason | Requestor | Assignee | Responsible Organization | Change Description | Initiation Date | Need By Date | Approval Request Date | Approval Date | Change Implementation Date | Change Cancellation Date | Cancellation Comments | Estimated Eng Cost | Estimated Mfg Cost | Revised Item | Revised Item Description | UOM | Alternate BOM | New Revision | New Routing Revision | Revised Item Status | Early Effectivity Date | Effectivity Date | Implementation Date | Cancellation Date | Use Up Item | Use Up Plan | Disposition | Mrp Active | Update Wip | From Unit Number | Revised Item Comment | Open Jobs | Open Job List | Action | Op Seq | Item Seq | Component | Component Description | Component UOM | Old Op Seq | Old Quantity | New Quantity | Yield | WIP Supply Type | Supply Subinventory | Component Effectivity Date | Component Disable Date | Component Implementation Date
M1 | 1234 | Document | Open | Approved | Standard | Quality | Jonathan Smith |  | Design Engineering |  | 1997-08-19 |  | 19-Aug-0097 | 1997-08-19 11:27
M1 | CB-M1-1 | New Prod | Implemented | Approved | Standard |  |  |  |  | Changing Fastners | 2008-09-25 05:03 |  | 2008-09-25 05:10 | 2008-09-25 05:29 | 2008-09-25 05:59 |  |  |  |  | AT22124 | Chassis - Sentinel | Ea |  |  |  | Implemented | 2008-09-25 05:08 | 2008-09-25 05:59 | 2008-09-25 05:59 |  |  |  | No change required | Yes | [5 empty] | Change | 30 | 110 | CM96717 | Screws.Steel.32.Phillips | Ea | 30 | 36 | 50 | 1 | Operation Pull |  | 2008-09-25 05:59 |  | 2008-09-25 05:59
M1 | EC01 | MCO | Implemented | Approved | High | Quality | Steve Williams |  | Manufacturing Engineering | Component VI11415 quality issue | 2004-06-11 |  |  | 2004-06-11 | 2004-06-28 09:53 |  |  |  |  | VI40001 | Motherboard - 700 Series | Ea |  |  |  | Implemented | 2004-06-11 | 2004-06-28 09:53 | 2004-06-28 09:53 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 1 | 140 | VI11415A | PNP Transistor | Ea |  |  | 1 | 1 | Assembly Pull |  | 2004-06-28 09:53 |  | 2004-06-28 09:53
M1 | EC010 | Document | Implemented | Approved | Low | Cost | Steve Williams |  |  | Document change order for service manual | 2004-07-28 14:09 |  |  | 2004-07-28 14:10 | 2004-08-12 16:28 |  |  |  |  | VI40001 | Motherboard - 700 Series | Ea |  |  |  | Implemented | 2004-07-28 14:10 | 2004-08-12 16:28 | 2004-08-12 16:28 |  |  |  | No change required | Yes | Yes
M1 | EC011 | MCO | Open | Approved | Medium | Quality | Steve Williams |  |  | Component swap due to supplier pricing issue | 2004-08-16 16:29 |  |  | 2004-08-16 16:30 | [5 empty] | VI40001 | Motherboard - 700 Series | Ea |  |  |  | Open | 2004-08-16 16:30 | 2004-08-16 16:30 |  |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 1 | 180 | VI11399A | Jumper JUMP1X8 | Ea |  |  | 1 | 1 | Assembly Pull |  | 2004-08-16 16:30
M1 | EC011 | MCO | Open | Approved | Medium | Quality | Steve Williams |  |  | Component swap due to supplier pricing issue | 2004-08-16 16:29 |  |  | 2004-08-16 16:30 | [5 empty] | VI40001 | Motherboard - 700 Series | Ea |  |  |  | Open | 2004-08-16 16:30 | 2004-08-16 16:30 |  |  |  |  | No change required | Yes | Yes |  |  |  |  | Disable | 12 | 55 | VI11399 | Jumper JUMP1X8 | Ea | 12 | 1 |  | 1 | Assembly Pull |  | 2004-08-16 16:30 | 2004-08-16 16:30
M1 | EC012 | MCO | Open | Approved | High | Cost | Steve Williams |  |  | Component swap due to supplier pricing issue | 2004-08-16 16:31 |  |  | 2004-08-16 16:32 | [5 empty] | VI40001 | Motherboard - 700 Series | Ea |  |  |  | Open | 2004-08-16 16:33 | 2004-08-16 16:33 |  |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 1 | 190 | VI12618A | Capacitor 0.22uf, 10V | Ea |  |  | 1 | 1 | Assembly Pull |  | 2004-08-16 16:33
M1 | EC012 | MCO | Open | Approved | High | Cost | Steve Williams |  |  | Component swap due to supplier pricing issue | 2004-08-16 16:31 |  |  | 2004-08-16 16:32 | [5 empty] | VI40001 | Motherboard - 700 Series | Ea |  |  |  | Open | 2004-08-16 16:33 | 2004-08-16 16:33 |  |  |  |  | No change required | Yes | Yes |  |  |  |  | Disable | 12 | 35 | VI12618 | Capacitor 0.22uf, 10V | Ea | 12 | 1 |  | 1 | Assembly Pull |  | 2004-08-16 16:33 | 2004-08-16 16:33
M1 | EC013 | Document | Open | Approved | Low | Cost | Steve Williams |  |  | Document change order for service manual | 2004-08-16 16:35 |  |  | 2004-08-16 16:35 | [5 empty] | VI40001 | Motherboard - 700 Series | Ea |  |  |  | Open | 2004-08-16 16:35 | 2004-08-16 16:35 |  |  |  |  | No change required | Yes | Yes
M1 | EC014 | Document | Released | Not submitted for approval | Medium | Quality | Steve Williams | Steve Williams |  | Recovery Target Proposal | 2004-09-30 14:24 | 2004-09-30 15:00
M1 | EC02 | Document | Implemented | Approved | Low | Misc | Steve Williams |  | Manufacturing Engineering | Documentation to capture BOM changes for VI40001 | 2004-06-11 |  |  | 2004-06-11 | 2004-07-08 15:27 |  |  |  |  | VI40001 | Motherboard - 700 Series | Ea |  |  |  | Implemented | 2004-06-11 | 2004-07-08 15:27 | 2004-07-08 15:27 |  |  |  | No change required | Yes | Yes
M1 | EC03 | MCO | Cancelled | Approved | Medium | Quality | Steve Williams |  | Manufacturing Engineering |  | 2004-06-25 |  |  |  |  | 2004-07-07 14:36 | Wrong component effective date. |  |  | VI40001 | Motherboard - 700 Series | Ea |  |  |  | Cancelled | 2004-06-25 | 2004-06-25 15:20 |  | 2004-07-07 14:36 |  |  | No change required | Yes | Yes
M1 | EC03I | MCO | Cancelled | Not submitted for approval | Standard | Quality | Steve Williams |  | Manufacturing Engineering |  | 2004-07-08 15:30 |  |  |  |  | 2004-07-09 08:38 | refer to ECO3-I
M1 | EC04 | MCO | Implemented | Approved | Medium | Cost | Steve Williams |  | Manufacturing Engineering | Routing change for outsourcing VI11405 | 2004-06-26 |  |  | 2004-06-26 | 2004-07-08 15:29 |  |  |  |  | VI40001 | Motherboard - 700 Series | Ea |  |  |  | Implemented | 2004-06-26 | 2004-07-08 15:29 | 2004-07-08 15:29 |  |  |  | No change required | Yes | Yes
M1 | EC05 | Document | Implemented | Approved | Low | Cost | Steve Williams |  |  | Documentation to capture BOM changes for Service | 2004-06-26 |  |  | 2004-06-26 | 2004-07-20 13:19 |  |  |  |  | VI40001 | Motherboard - 700 Series | Ea |  |  |  | Implemented | 2004-06-26 | 2004-07-20 13:19 | 2004-07-20 13:19 |  |  |  | No change required | Yes | Yes
M1 | EC06 | MCO | Implemented | Approved | High | Quality | Steve Williams |  |  | Component VI10008 OEM quality issue | 2004-07-28 12:59 |  |  | 2004-07-28 13:11 | 2004-07-30 10:18 |  |  |  |  | VI40001 | Motherboard - 700 Series | Ea |  |  |  | Implemented | 2004-07-28 13:13 | 2004-07-30 10:18 | 2004-07-30 10:18 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 1 | 160 | VI10008A | 3.3 VQuad Switch | Ea |  |  | 1 | 1 | Assembly Pull |  | 2004-07-30 10:18 |  | 2004-07-30 10:18
M1 | EC07 | Document | Implemented | Approved | Low | Quality | Steve Williams |  |  | Documentation changes for service manual | 2004-07-28 13:15 |  |  | 2004-07-28 13:17 | 2004-07-30 10:20 |  |  |  |  | VI40001 | Motherboard - 700 Series | Ea |  |  |  | Implemented | 2004-07-28 13:17 | 2004-07-30 10:20 | 2004-07-30 10:20 |  |  |  | No change required | Yes | Yes
M1 | EC08 | MCO | Implemented | Approved | Medium | Cost | Steve Williams |  |  | BOM change for outsourcing VI12472 | 2004-07-28 13:52 |  |  | 2004-07-28 13:54 | 2004-08-05 16:40 |  |  |  |  | VI40001 | Motherboard - 700 Series | Ea |  |  |  | Implemented | 2004-07-28 13:54 | 2004-08-05 16:40 | 2004-08-05 16:40 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 1 | 170 | VI12472A | Serial EPROM Memory 3.3V | Ea |  |  | 1 | 1 | Assembly Pull |  | 2004-08-05 16:40 |  | 2004-08-05 16:40
M1 | EC09 | MCO | Implemented | Approved | High | Cost | Steve Williams |  |  | Routing change for outsourcing VI12472 | 2004-07-28 14:04 |  |  | 2004-07-28 14:08 | 2004-08-05 16:41 |  |  |  |  | VI40001 | Motherboard - 700 Series | Ea |  |  |  | Implemented | 2004-07-28 14:08 | 2004-08-05 16:41 | 2004-08-05 16:41 |  |  |  | No change required | Yes | Yes
M1 | ECO108 | ECO | Implemented | Approved | Standard |  | Steve Williams | Mary Robinson |  | Update motherboard and chassis option classes in the CN82441 primary manufacturing BOM to include the new motherboard VI40001 and its chassis | 2003-10-07 16:39 |  |  | 2003-10-21 12:52 | 2003-10-21 13:08 |  |  |  |  | OC86661 | PC Chassis Option Class | Ea |  |  |  | Implemented | 2003-10-07 | 2003-10-21 13:08 | 2003-10-21 13:08 |  |  |  | No change required | Yes | [5 empty] | Add | 1 | 20 | VI74953 | Desktop Chassis Model A243 | Ea |  |  | 1 | 1 | Assembly Pull |  | 2003-10-21 13:08 |  | 2003-10-21 13:08
M1 | ECO108 | ECO | Implemented | Approved | Standard |  | Steve Williams | Mary Robinson |  | Update motherboard and chassis option classes in the CN82441 primary manufacturing BOM to include the new motherboard VI40001 and its chassis | 2003-10-07 16:39 |  |  | 2003-10-21 12:52 | 2003-10-21 13:08 |  |  |  |  | OC87740 | Motherboard Option Class | Ea |  |  |  | Implemented | 2003-10-07 | 2003-10-21 13:08 | 2003-10-21 13:08 |  |  |  | No change required | Yes | [5 empty] | Add | 1 | 20 | VI40001 | Motherboard - 700 Series | Ea |  |  | 1 | 1 | Assembly Pull |  | 2003-10-21 13:08 |  | 2003-10-21 13:08
M1 | ECO110 | ECO | Open | Not submitted for approval | Standard |  | Steve Williams | Mary Robinson |  | Revise option classes - pending confirmation of supplier productivity. | 2003-10-08 09:52
M1 | ECO114 | ECO | Open | Not submitted for approval | High | Quality | Mary Robinson | Steve Williams | Design Engineering | This engineering change order replaces a capacitor 'VI10576' having a reference designator CAP1 on the VI40001 motherboard. The new capacitor has a tolerance of 10%, packaging type SM and is ROHS compliant. As a result of this change the motherboard continues to be interchangeable with all desktop assemblies. The motherboard and standard assembly desktop are being revised, through this change order to update some specification attributes, the motherboard BIOS, a technical design document and add a new motherboard MPN on its AML. | 2005-06-19 05:40 | [8 empty] | CN82441 | Sentinel System | Ea |  | C |  | Open |  | 2006-12-31 10:30 |  |  |  |  | No change required | Yes
M1 | ECO114 | ECO | Open | Not submitted for approval | High | Quality | Mary Robinson | Steve Williams | Design Engineering | This engineering change order replaces a capacitor 'VI10576' having a reference designator CAP1 on the VI40001 motherboard. The new capacitor has a tolerance of 10%, packaging type SM and is ROHS compliant. As a result of this change the motherboard continues to be interchangeable with all desktop assemblies. The motherboard and standard assembly desktop are being revised, through this change order to update some specification attributes, the motherboard BIOS, a technical design document and add a new motherboard MPN on its AML. | 2005-06-19 05:40 | [8 empty] | VI40001 | Motherboard - 700 Series | Ea | EBOM |  |  | Open |  | 2006-12-31 10:30 |  |  |  |  | No change required | Yes | Yes |  | EBOM changes to replace capacitor VI10576 with capacitor VI60000CAP, which has a higher tolerance of 10% and is ROHS Compliant |  |  | Disable | 1 | 260 | VI10576 | Capacitor,TA,22uF,10V,5%,SM,1206,B CASE | Ea | 1 | 1 |  | 1 | Assembly Pull |  | 2007-01-01 | 2007-01-01
M1 | ECO114 | ECO | Open | Not submitted for approval | High | Quality | Mary Robinson | Steve Williams | Design Engineering | This engineering change order replaces a capacitor 'VI10576' having a reference designator CAP1 on the VI40001 motherboard. The new capacitor has a tolerance of 10%, packaging type SM and is ROHS compliant. As a result of this change the motherboard continues to be interchangeable with all desktop assemblies. The motherboard and standard assembly desktop are being revised, through this change order to update some specification attributes, the motherboard BIOS, a technical design document and add a new motherboard MPN on its AML. | 2005-06-19 05:40 | [8 empty] | VI40001 | Motherboard - 700 Series | Ea | EBOM |  |  | Open |  | 2006-12-31 10:30 |  |  |  |  | No change required | Yes | Yes |  | EBOM changes to replace capacitor VI10576 with capacitor VI60000CAP, which has a higher tolerance of 10% and is ROHS Compliant |  |  | Add | 1 | 270 | VI60000CAP | Capacitor,TA,22uF,10V,10%,SM,1206,VCASE | Ea |  |  | 1 | 1 | Push |  | 2007-01-01
M1 | ECO114 | ECO | Open | Not submitted for approval | High | Quality | Mary Robinson | Steve Williams | Design Engineering | This engineering change order replaces a capacitor 'VI10576' having a reference designator CAP1 on the VI40001 motherboard. The new capacitor has a tolerance of 10%, packaging type SM and is ROHS compliant. As a result of this change the motherboard continues to be interchangeable with all desktop assemblies. The motherboard and standard assembly desktop are being revised, through this change order to update some specification attributes, the motherboard BIOS, a technical design document and add a new motherboard MPN on its AML. | 2005-06-19 05:40 | [8 empty] | VI40001 | Motherboard - 700 Series | Ea | MBOM |  |  | Open | 2005-06-19 | 2006-12-31 10:30 |  |  |  |  | No change required | Yes | Yes |  | MBOM changes to replace capacitor VI10576 with capacitor VI60000CAP, which has a higher tolerance of 10% and is ROHS Compliant |  |  | Disable | 1 | 240 | VI10576 | Capacitor,TA,22uF,10V,5%,SM,1206,B CASE | Ea | 1 | 1 |  | 1 | Assembly Pull |  | 2006-12-31 23:59 | 2006-12-31 10:30
M1 | ECO114 | ECO | Open | Not submitted for approval | High | Quality | Mary Robinson | Steve Williams | Design Engineering | This engineering change order replaces a capacitor 'VI10576' having a reference designator CAP1 on the VI40001 motherboard. The new capacitor has a tolerance of 10%, packaging type SM and is ROHS compliant. As a result of this change the motherboard continues to be interchangeable with all desktop assemblies. The motherboard and standard assembly desktop are being revised, through this change order to update some specification attributes, the motherboard BIOS, a technical design document and add a new motherboard MPN on its AML. | 2005-06-19 05:40 | [8 empty] | VI40001 | Motherboard - 700 Series | Ea | MBOM |  |  | Open | 2005-06-19 | 2006-12-31 10:30 |  |  |  |  | No change required | Yes | Yes |  | MBOM changes to replace capacitor VI10576 with capacitor VI60000CAP, which has a higher tolerance of 10% and is ROHS Compliant |  |  | Add | 1 | 270 | VI60000CAP | Capacitor,TA,22uF,10V,10%,SM,1206,VCASE | Ea |  |  | 1 | 1 | Push |  | 2006-12-31 23:59
M1 | ECO114 | ECO | Open | Not submitted for approval | High | Quality | Mary Robinson | Steve Williams | Design Engineering | This engineering change order replaces a capacitor 'VI10576' having a reference designator CAP1 on the VI40001 motherboard. The new capacitor has a tolerance of 10%, packaging type SM and is ROHS compliant. As a result of this change the motherboard continues to be interchangeable with all desktop assemblies. The motherboard and standard assembly desktop are being revised, through this change order to update some specification attributes, the motherboard BIOS, a technical design document and add a new motherboard MPN on its AML. | 2005-06-19 05:40 | [8 empty] | VI40001 | Motherboard - 700 Series | Ea |  | C |  | Open |  | 2006-12-31 10:30 |  |  |  |  | No change required | Yes
M1 | ECO3-1 | New Prod | Implemented | Approved | Standard |  |  |  |  | Change parts | 2004-07-09 08:31 |  | 2004-07-09 08:34 | 2004-07-09 08:35 | 2004-07-09 08:36 |  |  |  |  | VI40001 | Motherboard - 700 Series | Ea |  |  |  | Implemented | 2004-07-09 08:33 | 2004-07-09 08:36 | 2004-07-09 08:36 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 1 | 150 | VI11405A | Li-ion/Li-Polymer Battery Charger | Ea |  |  | 1 | 1 | Assembly Pull |  | 2004-07-09 08:36 |  | 2004-07-09 08:36
M1 | M1-1000 | Prod Chg | Open | Approved | Standard | Sales | Jonathan Smith |  | Design Engineering |  | 1997-05-14 |  |  | 1997-05-14 | [5 empty] | AS18947 | Sentinel Deluxe Desktop | Ea |  | B |  | Open | 1997-05-14 | 1997-10-01 |  |  |  |  | No change required | Yes | Yes |  |  | 1 | 246413 | Disable | 60 | 20 | CM15138 | Monitor - 17" | Ea | 60 | 1 |  | 1 | Operation Pull |  | 1997-10-01 | 1997-10-01
M1 | M1-1000 | Prod Chg | Open | Approved | Standard | Sales | Jonathan Smith |  | Design Engineering |  | 1997-05-14 |  |  | 1997-05-14 | [5 empty] | AS18947 | Sentinel Deluxe Desktop | Ea |  | B |  | Open | 1997-05-14 | 1997-10-01 |  |  |  |  | No change required | Yes | Yes |  |  |  | 246413 | Add | 60 | 21 | CM15140 | Monitor - 19" | Ea |  |  | 1 | 1 | Operation Pull |  | 1997-10-01
M1 | M1-1001 | Prod Chg | Open | Approved | Standard | Sales | Rajesh Gupta |  | Design Engineering |  | 1997-05-14 |  |  | 1997-05-14 | [5 empty] | AS18947 | Sentinel Deluxe Desktop | Ea |  | C |  | Open | 1997-05-14 | 1998-02-01 |  |  |  |  | No change required | Yes | Yes |  |  | 1 | 246413 | Disable | 60 | 21 | CM15140 | Monitor - 19" | Ea | 60 | 1 |  | 1 | Operation Pull |  | 1998-02-01 | 1998-02-01
M1 | M1-1001 | Prod Chg | Open | Approved | Standard | Sales | Rajesh Gupta |  | Design Engineering |  | 1997-05-14 |  |  | 1997-05-14 | [5 empty] | AS18947 | Sentinel Deluxe Desktop | Ea |  | C |  | Open | 1997-05-14 | 1998-02-01 |  |  |  |  | No change required | Yes | Yes |  |  |  | 246413 | Add | 60 | 22 | CM31556 | Monitor - 19" Flat | Ea |  |  | 1 | 1 | Operation Pull |  | 1998-02-01
M1 | M1-1002 | Prod Chg | Open | Rejected | Standard | Sales | David Olsen |  | Design Engineering |  | 1997-05-14 | [8 empty] | AS18947 | Sentinel Deluxe Desktop | Ea |  | D |  | Open | 1997-05-14 | 1998-06-01 |  |  |  |  | No change required |  | Yes |  |  | 1 | 246413 | Disable | 60 | 22 | CM31556 | Monitor - 19" Flat | Ea | 60 | 1 |  | 1 | Operation Pull |  | 1998-06-01 | 1998-06-01
M1 | M1-1002 | Prod Chg | Open | Rejected | Standard | Sales | David Olsen |  | Design Engineering |  | 1997-05-14 | [8 empty] | AS18947 | Sentinel Deluxe Desktop | Ea |  | D |  | Open | 1997-05-14 | 1998-06-01 |  |  |  |  | No change required |  | Yes |  |  |  | 246413 | Add | 60 | 23 | CM31558 | Monitor 21" (20" Viewable) High Resolution | Ea |  |  | 1 | 1 | Operation Pull |  | 1998-06-01
M1 | M1-1007 | New Prod | Open | Approved | Standard | [5 empty] | 1999-10-06 |  | 1999-10-06 | 1999-10-06 12:34
M1 | M1-1010 | New Prod | Open | Not submitted for approval | Standard |  |  |  |  | Testing docs and workflow | 2000-02-29
M1 | M1-1013 | New Prod | Open | Approved | Standard |  |  |  |  | Documentation Introduction | 2001-04-02 |  | 2001-04-02 | 2001-08-07 15:57
M1 | M1-1015 | Prod Chg | Scheduled | Approved | Standard | Cost |  |  | Manufacturing Engineering | Lower cost Mother Board | 2003-11-20 |  | 2003-11-20 | 2003-11-20 18:00 | [5 empty] | AS44400 | President Model Desktop PC | Ea |  |  |  | Scheduled | 2003-12-05 | 2003-11-20 17:58 |  |  |  |  | No change required | Yes | Yes |  |  |  |  | Disable | 30 | 80 | CM22473 | Motherboard - 600 Series | Ea | 30 | 1 |  | 1 | Operation Pull |  | 2003-11-20 17:58 | 2003-11-20 17:58
M1 | M1-1015 | Prod Chg | Scheduled | Approved | Standard | Cost |  |  | Manufacturing Engineering | Lower cost Mother Board | 2003-11-20 |  | 2003-11-20 | 2003-11-20 18:00 | [5 empty] | AS44400 | President Model Desktop PC | Ea |  |  |  | Scheduled | 2003-12-05 | 2003-11-20 17:58 |  |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 30 | 170 | CM44410 | Mother Board - President Model | Ea |  |  | 1 | 1 | Assembly Pull |  | 2003-11-20 17:58
M1 | M1-1016 | Prod Chg | Implemented | Approved | Standard | Cost |  |  | Design Engineering | Outsource Chassis Assembly - Cost Savings | 2003-11-20 |  | 2003-11-20 | 2003-11-20 18:18 | 2003-11-20 18:19 |  |  |  |  | AS44400 | President Model Desktop PC | Ea |  |  |  | Implemented | 2003-12-26 | 2003-11-20 18:19 | 2003-11-20 18:19 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 10 | 180 | CM74333 | Chassis - President Model | Ea |  |  | 1 | 1 | Assembly Pull |  | 2003-11-20 18:19 |  | 2003-11-20 18:19
M1 | M1-1017 | Prod Chg | Implemented | Approved | Standard | Cost |  |  |  | Replace Motherboard with Lower Cost Unit | 2004-05-07 |  | 2004-05-07 | 2004-05-07 10:58 | 2004-05-07 10:59 |  |  |  |  | AS44400 | President Model Desktop PC | Ea |  |  |  | Implemented | 2004-05-07 | 2004-05-07 10:59 | 2004-05-07 10:59 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 30 | 190 | CM35682 | Motherboard - 500 Series | Ea |  |  | 1 | 1 | Operation Pull |  | 2004-05-07 10:59 |  | 2004-05-07 10:59
M1 | M1-1018 | Prod Chg | Implemented | Approved | Standard | Cost |  |  |  | Replace Battery | 2004-05-14 |  | 2004-05-14 | 2004-05-14 06:01 | 2004-05-14 06:02 |  |  |  |  | AS44400 | President Model Desktop PC | Ea |  |  |  | Implemented | 2004-05-14 | 2004-05-14 06:02 | 2004-05-14 06:02 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 30 | 200 | CM11222 | Battery - Extended Life | Ea |  |  | 1 | 1 | Assembly Pull |  | 2004-05-14 06:02 |  | 2004-05-14 06:02
M1 | M1-1021 | Prod Chg | Implemented | Approved | [6 empty] | 2004-09-15 08:02 |  |  | 2004-09-15 08:03 | 2004-09-15 08:06 |  |  |  |  | AS65103 | Vision Pad - Gold | Ea |  |  |  | Implemented | 2004-09-15 08:05 | 2005-05-31 | 2004-09-15 08:06 |  |  |  | No change required | Yes | Yes |  |  |  |  | Change | 1011 | 20 | CM60257 | RAM - 128MB | Ea | 1010 | 1 | 2 | 1 | Operation Pull | RIP | 2005-05-31 |  | 2005-05-31
M1 | M1-1023 | Prod Chg | Implemented | Approved | Urgent | Cost |  |  |  | Move Mother Board manufacture in house | 2005-03-08 10:22 |  | 2005-03-08 10:29 | 2005-03-08 10:30 | 2005-03-08 10:31 |  |  |  |  | XA1000 | GameGirl | Ea |  |  |  | Implemented | 2005-03-08 10:23 | 2005-03-08 10:31 | 2005-03-08 10:31 |  |  |  | No change required | Yes | Yes |  |  | 3 | 242841, 243646, 243645 | Add | 11 | 70 | XC1101 | GG Circuit Board | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-03-08 10:31 |  | 2005-03-08 10:31
M1 | M1-1023 | Prod Chg | Implemented | Approved | Urgent | Cost |  |  |  | Move Mother Board manufacture in house | 2005-03-08 10:22 |  | 2005-03-08 10:29 | 2005-03-08 10:30 | 2005-03-08 10:31 |  |  |  |  | XA1000 | GameGirl | Ea |  |  |  | Implemented | 2005-03-08 10:23 | 2005-03-08 10:31 | 2005-03-08 10:31 |  |  |  | No change required | Yes | Yes |  |  |  | 242841, 243646, 243645 | Add | 11 | 80 | XC1102 | Resistor | Ea |  |  | 6 | 1 | Assembly Pull | RIP | 2005-03-08 10:31 | 2005-05-19 05:14 | 2005-03-08 10:31
M1 | M1-1023 | Prod Chg | Implemented | Approved | Urgent | Cost |  |  |  | Move Mother Board manufacture in house | 2005-03-08 10:22 |  | 2005-03-08 10:29 | 2005-03-08 10:30 | 2005-03-08 10:31 |  |  |  |  | XA1000 | GameGirl | Ea |  |  |  | Implemented | 2005-03-08 10:23 | 2005-03-08 10:31 | 2005-03-08 10:31 |  |  |  | No change required | Yes | Yes |  |  |  | 242841, 243646, 243645 | Add | 11 | 90 | XC1103 | Capacitor | Ea |  |  | 3 | 1 | Assembly Pull | RIP | 2005-03-08 10:31 |  | 2005-03-08 10:31
M1 | M1-1023 | Prod Chg | Implemented | Approved | Urgent | Cost |  |  |  | Move Mother Board manufacture in house | 2005-03-08 10:22 |  | 2005-03-08 10:29 | 2005-03-08 10:30 | 2005-03-08 10:31 |  |  |  |  | XA1000 | GameGirl | Ea |  |  |  | Implemented | 2005-03-08 10:23 | 2005-03-08 10:31 | 2005-03-08 10:31 |  |  |  | No change required | Yes | Yes |  |  |  | 242841, 243646, 243645 | Add | 11 | 100 | XC1104 | RAM | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-03-08 10:31 |  | 2005-03-08 10:31
M1 | M1-1023 | Prod Chg | Implemented | Approved | Urgent | Cost |  |  |  | Move Mother Board manufacture in house | 2005-03-08 10:22 |  | 2005-03-08 10:29 | 2005-03-08 10:30 | 2005-03-08 10:31 |  |  |  |  | XA1000 | GameGirl | Ea |  |  |  | Implemented | 2005-03-08 10:23 | 2005-03-08 10:31 | 2005-03-08 10:31 |  |  |  | No change required | Yes | Yes |  |  |  | 242841, 243646, 243645 | Add | 11 | 110 | XC1105 | Diode | Ea |  |  | 6 | 1 | Assembly Pull | RIP | 2005-03-08 10:31 |  | 2005-03-08 10:31
M1 | M1-1023 | Prod Chg | Implemented | Approved | Urgent | Cost |  |  |  | Move Mother Board manufacture in house | 2005-03-08 10:22 |  | 2005-03-08 10:29 | 2005-03-08 10:30 | 2005-03-08 10:31 |  |  |  |  | XA1000 | GameGirl | Ea |  |  |  | Implemented | 2005-03-08 10:23 | 2005-03-08 10:31 | 2005-03-08 10:31 |  |  |  | No change required | Yes | Yes |  |  |  | 242841, 243646, 243645 | Add | 11 | 120 | XC1106 | Label | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-03-08 10:31 |  | 2005-03-08 10:31
M1 | M1-1023 | Prod Chg | Implemented | Approved | Urgent | Cost |  |  |  | Move Mother Board manufacture in house | 2005-03-08 10:22 |  | 2005-03-08 10:29 | 2005-03-08 10:30 | 2005-03-08 10:31 |  |  |  |  | XA1000 | GameGirl | Ea |  |  |  | Implemented | 2005-03-08 10:23 | 2005-03-08 10:31 | 2005-03-08 10:31 |  |  |  | No change required | Yes | Yes |  |  |  | 242841, 243646, 243645 | Add | 11 | 130 | XC1107 | DIP Switch | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-03-08 10:31 |  | 2005-03-08 10:31
M1 | M1-1024 | Prod Chg | Implemented | Approved | Standard | Perform |  |  |  | Mother Board production being moved in house. | 2005-03-08 10:36 |  | 2005-03-08 10:49 | 2005-03-08 10:49 | 2005-03-14 05:24 |  |  |  |  | XA4000 | Standard Laptop | Ea |  |  |  | Implemented | 2005-03-08 10:43 | 2005-03-14 05:24 | 2005-03-14 05:24 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 11 | 120 | XC4101 | Standard Laptop Circuit Board | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-03-14 05:24 |  | 2005-03-14 05:24
M1 | M1-1024 | Prod Chg | Implemented | Approved | Standard | Perform |  |  |  | Mother Board production being moved in house. | 2005-03-08 10:36 |  | 2005-03-08 10:49 | 2005-03-08 10:49 | 2005-03-14 05:24 |  |  |  |  | XA4000 | Standard Laptop | Ea |  |  |  | Implemented | 2005-03-08 10:43 | 2005-03-14 05:24 | 2005-03-14 05:24 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 11 | 130 | XC4102 | Resistor | Ea |  |  | 6 | 1 | Assembly Pull | RIP | 2005-03-14 05:24 | 2005-05-23 06:46 | 2005-03-14 05:24
M1 | M1-1024 | Prod Chg | Implemented | Approved | Standard | Perform |  |  |  | Mother Board production being moved in house. | 2005-03-08 10:36 |  | 2005-03-08 10:49 | 2005-03-08 10:49 | 2005-03-14 05:24 |  |  |  |  | XA4000 | Standard Laptop | Ea |  |  |  | Implemented | 2005-03-08 10:43 | 2005-03-14 05:24 | 2005-03-14 05:24 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 11 | 140 | XC4103 | Capacitor | Ea |  |  | 3 | 1 | Assembly Pull | RIP | 2005-03-14 05:24 |  | 2005-03-14 05:24
M1 | M1-1024 | Prod Chg | Implemented | Approved | Standard | Perform |  |  |  | Mother Board production being moved in house. | 2005-03-08 10:36 |  | 2005-03-08 10:49 | 2005-03-08 10:49 | 2005-03-14 05:24 |  |  |  |  | XA4000 | Standard Laptop | Ea |  |  |  | Implemented | 2005-03-08 10:43 | 2005-03-14 05:24 | 2005-03-14 05:24 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 11 | 150 | XC4104 | RAM | Ea |  |  | 4 | 1 | Assembly Pull | RIP | 2005-03-14 05:24 |  | 2005-03-14 05:24
M1 | M1-1024 | Prod Chg | Implemented | Approved | Standard | Perform |  |  |  | Mother Board production being moved in house. | 2005-03-08 10:36 |  | 2005-03-08 10:49 | 2005-03-08 10:49 | 2005-03-14 05:24 |  |  |  |  | XA4000 | Standard Laptop | Ea |  |  |  | Implemented | 2005-03-08 10:43 | 2005-03-14 05:24 | 2005-03-14 05:24 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 11 | 160 | XC4105 | Diode | Ea |  |  | 12 | 1 | Assembly Pull | RIP | 2005-03-14 05:24 |  | 2005-03-14 05:24
M1 | M1-1024 | Prod Chg | Implemented | Approved | Standard | Perform |  |  |  | Mother Board production being moved in house. | 2005-03-08 10:36 |  | 2005-03-08 10:49 | 2005-03-08 10:49 | 2005-03-14 05:24 |  |  |  |  | XA4000 | Standard Laptop | Ea |  |  |  | Implemented | 2005-03-08 10:43 | 2005-03-14 05:24 | 2005-03-14 05:24 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 11 | 170 | XC4106 | Label | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-03-14 05:24 |  | 2005-03-14 05:24
M1 | M1-1024 | Prod Chg | Implemented | Approved | Standard | Perform |  |  |  | Mother Board production being moved in house. | 2005-03-08 10:36 |  | 2005-03-08 10:49 | 2005-03-08 10:49 | 2005-03-14 05:24 |  |  |  |  | XA4000 | Standard Laptop | Ea |  |  |  | Implemented | 2005-03-08 10:43 | 2005-03-14 05:24 | 2005-03-14 05:24 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 11 | 180 | XC4107 | DIP Switch | Ea |  |  | 2 | 1 | Assembly Pull | RIP | 2005-03-14 05:24 |  | 2005-03-14 05:24
M1 | M1-1025 | Prod Chg | Implemented | Approved | Low | Quality |  |  |  | Bring Mother Board Production In House | 2005-03-09 07:14 |  |  | 2005-03-09 07:51 | 2005-03-23 13:01 |  |  |  |  | XA6000 | Lite Desktop | Ea |  |  |  | Implemented | 2005-03-09 07:16 | 2005-03-23 13:01 | 2005-03-23 13:01 |  |  |  | No change required | Yes | Yes |  |  | 1 | 242541 | Add | 11 | 120 | XC6101 | Lite Desktop Circuit Board | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-03-23 13:01 |  | 2005-03-23 13:01
M1 | M1-1025 | Prod Chg | Implemented | Approved | Low | Quality |  |  |  | Bring Mother Board Production In House | 2005-03-09 07:14 |  |  | 2005-03-09 07:51 | 2005-03-23 13:01 |  |  |  |  | XA6000 | Lite Desktop | Ea |  |  |  | Implemented | 2005-03-09 07:16 | 2005-03-23 13:01 | 2005-03-23 13:01 |  |  |  | No change required | Yes | Yes |  |  |  | 242541 | Add | 11 | 130 | XC6102 | Resistor | Ea |  |  | 6 | 1 | Assembly Pull | RIP | 2005-03-23 13:01 | 2005-06-10 05:00 | 2005-03-23 13:01
M1 | M1-1025 | Prod Chg | Implemented | Approved | Low | Quality |  |  |  | Bring Mother Board Production In House | 2005-03-09 07:14 |  |  | 2005-03-09 07:51 | 2005-03-23 13:01 |  |  |  |  | XA6000 | Lite Desktop | Ea |  |  |  | Implemented | 2005-03-09 07:16 | 2005-03-23 13:01 | 2005-03-23 13:01 |  |  |  | No change required | Yes | Yes |  |  |  | 242541 | Add | 11 | 140 | XC6103 | Capacitor | Ea |  |  | 3 | 1 | Assembly Pull | RIP | 2005-03-23 13:01 |  | 2005-03-23 13:01
M1 | M1-1025 | Prod Chg | Implemented | Approved | Low | Quality |  |  |  | Bring Mother Board Production In House | 2005-03-09 07:14 |  |  | 2005-03-09 07:51 | 2005-03-23 13:01 |  |  |  |  | XA6000 | Lite Desktop | Ea |  |  |  | Implemented | 2005-03-09 07:16 | 2005-03-23 13:01 | 2005-03-23 13:01 |  |  |  | No change required | Yes | Yes |  |  |  | 242541 | Add | 11 | 150 | XC6104 | RAM | Ea |  |  | 2 | 1 | Assembly Pull | RIP | 2005-03-23 13:01 |  | 2005-03-23 13:01
M1 | M1-1025 | Prod Chg | Implemented | Approved | Low | Quality |  |  |  | Bring Mother Board Production In House | 2005-03-09 07:14 |  |  | 2005-03-09 07:51 | 2005-03-23 13:01 |  |  |  |  | XA6000 | Lite Desktop | Ea |  |  |  | Implemented | 2005-03-09 07:16 | 2005-03-23 13:01 | 2005-03-23 13:01 |  |  |  | No change required | Yes | Yes |  |  |  | 242541 | Add | 11 | 160 | XC6105 | Diode | Ea |  |  | 6 | 1 | Assembly Pull | RIP | 2005-03-23 13:01 |  | 2005-03-23 13:01
M1 | M1-1025 | Prod Chg | Implemented | Approved | Low | Quality |  |  |  | Bring Mother Board Production In House | 2005-03-09 07:14 |  |  | 2005-03-09 07:51 | 2005-03-23 13:01 |  |  |  |  | XA6000 | Lite Desktop | Ea |  |  |  | Implemented | 2005-03-09 07:16 | 2005-03-23 13:01 | 2005-03-23 13:01 |  |  |  | No change required | Yes | Yes |  |  |  | 242541 | Add | 11 | 170 | XC6106 | Label | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-03-23 13:01 |  | 2005-03-23 13:01
M1 | M1-1025 | Prod Chg | Implemented | Approved | Low | Quality |  |  |  | Bring Mother Board Production In House | 2005-03-09 07:14 |  |  | 2005-03-09 07:51 | 2005-03-23 13:01 |  |  |  |  | XA6000 | Lite Desktop | Ea |  |  |  | Implemented | 2005-03-09 07:16 | 2005-03-23 13:01 | 2005-03-23 13:01 |  |  |  | No change required | Yes | Yes |  |  |  | 242541 | Add | 11 | 180 | XC6107 | DIP Switch | Ea |  |  | 2 | 1 | Assembly Pull | RIP | 2005-03-23 13:01 |  | 2005-03-23 13:01
M1 | M1-1026 | Prod Chg | Implemented | Approved | Standard | Cost |  |  |  | Replace Monitor - Lower Cost | 2005-03-24 07:58 |  | 2005-03-24 08:00 | 2005-03-24 08:03 | 2005-04-05 05:42 |  |  |  |  | XA7000 | Standard Desktop | Ea |  |  |  | Implemented | 2005-03-24 07:58 | 2005-04-05 05:42 | 2005-04-05 05:42 |  |  |  | No change required | Yes | Yes |  |  | 1 | 242843 | Add | 10 | 30 | XC7102 | Std. Desktop Monitor II | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-04-05 05:42 |  | 2005-04-05 05:42
M1 | M1-1027 | Prod Chg | Implemented | Approved | Standard | Cost |  |  |  | Replace Monitor - Lower Cost | 2005-03-24 08:00 |  | 2005-03-24 08:03 | 2005-03-24 08:03 | 2005-04-07 11:12 |  |  |  |  | XA8000 | Deluxe Desktop | Ea |  |  |  | Implemented | 2005-03-24 08:01 | 2005-04-07 11:12 | 2005-04-07 11:12 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 10 | 30 | XC8102 | Deluxe Desktop Monitor II | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-04-07 11:12 |  | 2005-04-07 11:12
M1 | M1-1028 | Prod Chg | Implemented | Approved | Standard | Safety |  |  |  | Replace recalled Power Supply | 2005-04-14 09:26 |  | 2005-04-14 09:28 | 2005-04-14 09:29 | 2005-05-02 11:22 |  |  |  |  | XA5000 | Deluxe Laptop | Ea |  |  |  | Implemented | 2005-04-14 09:27 | 2005-05-02 11:22 | 2005-05-02 11:22 |  |  |  | No change required | Yes | Yes |  |  | 1 | 242842 | Add | 10 | 80 | XC5107 | Deluxe Laptop Power Supply | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-05-02 11:22 |  | 2005-05-02 11:22
M1 | M1-1029 | Prod Chg | Scheduled | Approved | Standard | Quality |  |  |  | Add Pen Tray | 2005-04-15 06:00 |  | 2005-04-15 06:04 | 2005-04-15 06:04 | [5 empty] | CN10000 | Pen Watch Clip Model | Ea |  |  |  | Scheduled | 2005-04-15 06:03 | 2006-12-29 06:02 |  |  |  |  | No change required | Yes | [5 empty] | Change | 1010 | 40 | CM14000 | Pen Model Tray | Ea | 1010 | 1 | 2 | 1 | Assembly Pull | LOP1 | 2006-12-29 06:02
M1 | M1-1030 | Prod Chg | Cancelled | Processing error | Standard | Function |  |  |  | Additional resistors - functional improvement | 2005-05-17 06:45 |  | 2005-05-17 06:51 |  |  | 2005-05-17 07:07 | process error |  |  | XA1000 | GameGirl | Ea |  |  |  | Cancelled | 2005-05-17 06:46 | 2005-05-17 06:46 |  | 2005-05-17 07:07 |  |  | No change required | Yes | Yes |  |  | 3 | 242841, 243646, 243645
M1 | M1-1031 | Prod Chg | Implemented | Approved | Standard | Function |  |  |  | Add resistors | 2005-05-17 07:04 |  | 2005-05-17 07:08 | 2005-05-17 07:09 | 2005-05-19 05:14 |  |  |  |  | XA1000 | GameGirl | Ea |  |  |  | Implemented | 2005-05-17 07:07 | 2005-05-19 05:14 | 2005-05-19 05:14 |  |  |  | No change required | Yes | Yes |  |  | 3 | 242841, 243646, 243645 | Change | 11 | 80 | XC1102 | Resistor | Ea | 11 | 6 | 9 | 1 | Assembly Pull | RIP | 2005-05-19 05:14 |  | 2005-05-19 05:14
M1 | M1-1032 | Prod Chg | Implemented | Approved | Standard | Function |  |  |  | Add resistors | 2005-05-17 07:09 |  | 2005-05-17 07:10 | 2005-05-17 07:10 | 2005-05-23 06:46 |  |  |  |  | XA4000 | Standard Laptop | Ea |  |  |  | Implemented | 2005-05-17 07:09 | 2005-05-23 06:46 | 2005-05-23 06:46 |  |  |  | No change required | Yes | Yes |  |  |  |  | Change | 11 | 130 | XC4102 | Resistor | Ea | 11 | 6 | 9 | 1 | Assembly Pull | RIP | 2005-05-23 06:46 |  | 2005-05-23 06:46
M1 | M1-1033 | Prod Chg | Implemented | Approved | Standard | Function |  |  |  | Add resistors | 2005-05-17 07:10 |  | 2005-05-17 07:12 | 2005-05-17 07:12 | 2005-06-10 05:00 |  |  |  |  | XA6000 | Lite Desktop | Ea |  |  |  | Implemented | 2005-05-17 07:11 | 2005-06-10 05:00 | 2005-06-10 05:00 |  |  |  | No change required | Yes | Yes |  |  | 1 | 242541 | Change | 11 | 130 | XC6102 | Resistor | Ea | 11 | 6 | 9 | 1 | Assembly Pull | RIP | 2005-06-10 05:00 |  | 2005-06-10 05:00
M1 | M1-1034 | Prod Chg | Implemented | Approved | Standard | Function |  |  | Design Engineering | Replace Sensor - Functional Improvement | 2005-05-18 12:25 |  | 2005-05-18 12:30 | 2005-05-18 12:30 | 2005-05-18 12:31 |  |  |  |  | MDA0001 | Blood Glucose Monitor | Ea |  |  |  | Implemented | 2005-05-18 12:27 | 2005-05-18 12:31 | 2005-05-18 12:31 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 1 | 40 | MDC0013 | BGM Sensor | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-05-18 12:31 |  | 2005-05-18 12:31
M1 | M1-1035 | Prod Chg | Implemented | Approved | Standard | Style |  |  |  | Updated Ethernet Card | 2005-06-15 08:21 |  | 2005-06-15 08:24 | 2005-06-15 08:27 | 2005-07-01 07:33 |  |  |  |  | XA7000 | Standard Desktop | Ea |  |  |  | Implemented | 2005-06-15 08:22 | 2005-07-01 07:33 | 2005-07-01 07:33 |  |  |  | No change required | Yes | Yes |  |  | 1 | 242843 | Add | 10 | 120 | XC7020 | Std. Desktop Ethernet Card | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-07-01 07:33 |  | 2005-07-01 07:33
M1 | M1-1036 | Prod Chg | Implemented | Approved | Standard | Style |  |  |  | Update Ethernet Card | 2005-06-15 08:21 |  | 2005-06-15 08:27 | 2005-06-15 08:27 | 2005-07-01 07:35 |  |  |  |  | XA8000 | Deluxe Desktop | Ea |  |  |  | Implemented | 2005-06-15 08:25 | 2005-07-01 07:35 | 2005-07-01 07:35 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 10 | 120 | XC8020 | DLX. Desktop Ethernet Card | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-07-01 07:35 |  | 2005-07-01 07:35
M1 | M1-1037 | Prod Chg | Implemented | Approved | Standard | Cost |  |  |  | Replace Motherboard with updated and lower cost unit | 2005-08-31 06:35 |  | 2005-08-31 06:38 | 2005-08-31 06:40 | 2005-09-06 07:01 |  |  |  |  | XA5000 | Deluxe Laptop | Ea |  |  |  | Implemented | 2005-08-31 06:36 | 2005-09-06 07:01 | 2005-09-06 07:01 |  |  |  | No change required | Yes | Yes |  |  | 1 | 242842 | Add | 10 | 20 | XC5030 | Deluxe Laptop Motherboard II | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-09-06 07:01 |  | 2005-09-06 07:01
M1 | M1-1038 | Prod Chg | Implemented | Approved | Standard | Function |  |  |  | Replace controller with updated model | 2005-08-31 06:59 |  | 2005-08-31 07:01 | 2005-08-31 07:02 | 2005-09-09 06:57 |  |  |  |  | XA1000 | GameGirl | Ea |  |  |  | Implemented | 2005-08-31 07:00 | 2005-09-09 06:57 | 2005-09-09 06:57 |  |  |  | No change required | Yes | Yes |  |  | 3 | 242841, 243646, 243645 | Add | 10 | 40 | XC1120 | Game Girl Controller II | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-09-09 06:57 |  | 2005-09-09 06:57
M1 | M1-1039 | Prod Chg | Implemented | Approved | Standard | Function |  |  |  | Upgrade Monitor | 2005-10-17 09:12 |  | 2005-11-01 07:37 | 2005-11-01 07:37 | 2005-11-01 07:38 |  |  |  |  | XA4000 | Standard Laptop | Ea |  |  |  | Implemented | 2005-10-17 09:16 | 2005-11-01 09:13 | 2005-11-01 07:38 |  |  |  | No change required | Yes | Yes |  |  |  |  | Add | 10 | 30 | XC4120 | Standard Laptop Monitor | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-11-01 09:13 |  | 2005-11-01 07:38
M1 | M1-1040 | Prod Chg | Implemented | Approved | Standard | Function |  |  |  | Upgrade Monitor | 2005-10-17 09:18 |  | 2005-11-01 07:32 | 2005-11-01 07:33 | 2005-11-01 07:34 |  |  |  |  | XA5000 | Deluxe Laptop | Ea |  |  |  | Implemented | 2005-10-17 09:20 | 2005-11-01 09:19 | 2005-11-01 07:34 |  |  |  | No change required | Yes | Yes |  |  | 1 | 242842 | Add | 10 | 30 | XC5120 | Deluxe Lartop Monitor | Ea |  |  | 1 | 1 | Assembly Pull | RIP | 2005-11-01 09:19 |  | 2005-11-01 07:34

## Parameters
Blitz Report™ | ENG Engineering Change Orders
Build Date | 2026-10-10 18:34
Database Name | VIS
Run Date | 2026-10-15 02:25
Request Id | 5994287
User Name | OPERATIONS (Pat Stock)
Responsibility | Inventory
Sql | select mp.organization_code, eec.change_notice change_notice, ecotv.type_name change_type, xxen_util.meaning(eec.status_type,'ECG_ECN_STATUS',700) change_status, xxen_util.meaning(eec.approval_status_type,'ENG_ECN_APPROVAL_STATUS',700) approval_status, eec.priority_code priority, eec.reason_code reason, (select hp.party_name from hz_parties hp where eec.requestor_id=hp.party_id) requestor, (select hp.party_name from hz_parties hp where eec.assignee_id=hp.party_id) assignee, (select haouv.name from hr_all_organization_units_vl haouv where eec.responsible_organization_id=haouv.organization_id) responsible_organization, eec.description change_description, eec.initiation_date, eec.need_by_date, eec.approval_request_date, eec.approval_date, eec.implementation_date change_implementation_date, eec.cancellation_date change_cancellation_date, eec.cancellation_comments, decode(row_number() over (partition by eec.organization_id, eec.change_notice order by msiv.concatenated_segments, eri.revised_item_sequence_id , bcb.operation_seq_num, bcb.item_num, bcb.component_sequence_id),1,eec.estimated_eng_cost) estimated_eng_cost, decode(row_number() over (partition by eec.organization_id, eec.change_notice order by msiv.concatenated_segments, eri.revised_item_sequence_id , bcb.operation_seq_num, bcb.item_num, bcb.component_sequence_id),1,eec.estimated_mfg_cost) estimated_mfg_cost, msiv.concatenated_segments revised_item, msiv.description revised_item_description, msiv.primary_uom_code uom, (select bsb.alternate_bom_designator from bom_structures_b bsb where eri.bill_sequence_id=bsb.bill_sequence_id) alternate_bom, eri.new_item_revision new_revision, eri.new_routing_revision, xxen_util.meaning(eri.status_type,'ECG_ECN_STATUS',700) revised_item_status, eri.early_schedule_date early_effectivity_date, eri.scheduled_date effectivity_date, eri.implementation_date, eri.cancellation_date, (select msiv2.concatenated_segments from mtl_system_items_vl msiv2 where eri.use_up_item_id=msiv2.inventory_item_id and eri.organization_id=msiv2.organization_id) use_up_item, eri.use_up_plan_name use_up_plan, xxen_util.meaning(eri.disposition_type,'ECG_MATERIAL_DISPOSITION',700) disposition, xxen_util.yes(decode(eri.mrp_active,1,'Y')) mrp_active, xxen_util.yes(decode(eri.update_wip,1,'Y')) update_wip, eri.from_end_item_unit_number from_unit_number, eri.descriptive_text revised_item_comment, decode(row_number() over (partition by eec.organization_id, eec.change_notice, eri.revised_item_sequence_id order by eri.revised_item_sequence_id , bcb.operation_seq_num, bcb.item_num, bcb.component_sequence_id),1,wdj.open_jobs) open_jobs, wdj.open_job_list , xxen_util.meaning(bcb.acd_type,'ECG_ACTION',700) action, bcb.operation_seq_num op_seq, bcb.item_num item_seq, (select msiv3.concatenated_segments from mtl_system_items_vl msiv3 where bcb.component_item_id=msiv3.inventory_item_id and eri.organization_id=msiv3.organization_id) component, (select msiv3.description from mtl_system_items_vl msiv3 where bcb.component_item_id=msiv3.inventory_item_id and eri.organization_id=msiv3.organization_id) component_description, (select msiv3.primary_uom_code from mtl_system_items_vl msiv3 where bcb.component_item_id=msiv3.inventory_item_id and eri.organization_id=msiv3.organization_id) component_uom, (select bcb2.operation_seq_num from bom_components_b bcb2 where bcb.old_component_sequence_id=bcb2.component_sequence_id and bcb.acd_type in (2,3)) old_op_seq, (select bcb2.component_quantity from bom_components_b bcb2 where bcb.old_component_sequence_id=bcb2.component_sequence_id and bcb.acd_type in (2,3)) old_quantity, decode(bcb.acd_type,3,to_number(null),bcb.component_quantity) new_quantity, bcb.component_yield_factor yield, xxen_util.meaning(bcb.wip_supply_type,'WIP_SUPPLY',700) wip_supply_type, bcb.supply_subinventory, bcb.effectivity_date component_effectivity_date, bcb.disable_date component_disable_date, bcb.implementation_date component_implementation_date from mtl_parameters mp, eng_engineering_changes eec, eng_change_order_types_vl ecotv, eng_revised_items eri, mtl_system_items_vl msiv, ( select y.organization_id, y.primary_item_id, count(*) open_jobs, listagg(case when y.rn<=15 then y.wip_entity_name end,', ') within group (order by y.rn) open_job_list from ( select wdj.organization_id, wdj.primary_item_id, we.wip_entity_name, row_number() over (partition by wdj.organization_id, wdj.primary_item_id order by wdj.scheduled_start_date, we.wip_entity_name) rn from wip_discrete_jobs wdj, wip_entities we where wdj.status_type in (1,3,6) and (wdj.organization_id,wdj.primary_item_id) in (select eri.organization_id, eri.revised_item_id from eng_revised_items eri) and wdj.wip_entity_id=we.wip_entity_id ) y group by y.organization_id, y.primary_item_id ) wdj , bom_components_b bcb where mp.organization_code=:organization_code and 1=1 and mp.organization_id in (select oav.organization_id from org_access_view oav where oav.resp_application_id=fnd_global.resp_appl_id and oav.responsibility_id=fnd_global.resp_id) and mp.organization_id=eec.organization_id and eec.change_order_type_id=ecotv.change_order_type_id and ecotv.base_change_mgmt_type_code='CHANGE_ORDER' and eec.change_notice=eri.change_notice(+) and eec.organization_id=eri.organization_id(+) and eri.revised_item_id=msiv.inventory_item_id(+) and eri.organization_id=msiv.organization_id(+) and eri.organization_id=wdj.organization_id(+) and eri.revised_item_id=wdj.primary_item_id(+) and eri.revised_item_sequence_id=bcb.revised_item_sequence_id(+) order by mp.organization_code, eec.change_notice, msiv.concatenated_segments, eri.revised_item_sequence_id , bcb.operation_seq_num, bcb.item_num, bcb.component_sequence_id
Record Count | 80
Organization Code | M1
Show Component Changes | Yes